PROJECT MANAGEMENT PLAN

Project ID INV-02

| PLANNED DURATION 8 planned working days | TRACKER BASELINE DATE 15 October 2026 | TRACKING APPROACH Update status, completion date, issues and Git commit as work proceeds |
| --- | --- | --- |

Tracking instructions

Record each task’s status, actual completion date, issues and associated Git commit as work proceeds.

Status values: Complete |  In progress |  Blocked  |  Planned

| ID | Task | Expected output | Status | Completion date | Issues / notes |
| --- | --- | --- | --- | --- | --- |
| PM-01 | Confirm scope and project plan | Approved project scope | Completed | 2026-10-15 | Baseline proposal and folder structure prepared; source CSV still absent. |
| PM-02 | Source and document dataset | Raw dataset and source record | completed | 2026 – 10 - 15 | sales_data.csv is not present; verify source and licence before use. |
| PM-03 | Profile dataset and inspect fields | Initial data quality report | completed | 2026 – 10 - 15 | Requires the source CSV; proposal profile has not been independently verified. |
| PM-04 | Clean and prepare data in Excel | Cleaned dataset | completed | 2026 – 10 - 16 | Preserve raw source; requires PM-02 and PM-03. |
| PM-05 | Validate data and calculations | Validation checklist | completed | 2026 – 10 - | Validate record grain and calculation rules on actual data. |
| PM-06 | Create Excel calculations and PivotTables | Analysis workbook | Planned | — | Build after data cleaning and validation. |
| PM-07 | Complete exploratory analysis | Initial analytical findings | Planned | — | Findings must be supported by validated data. |
| PM-08 | Compare products, stores, regions, and periods | Comparative analysis | Planned | — | Check completeness and comparable periods. |
| PM-09 | Define and validate KPIs | KPI reference sheet | Planned | — | Validate definitions and aggregation before dashboard use. |
| PM-10 | Build Power BI dashboard | Interactive dashboard | Planned | — | Requires validated data and KPIs. |
| PM-11 | Interpret results and prepare recommendations | Business insights report | Planned | — | Do not infer stockouts, lost sales, or causation without evidence. |
| PM-12 | Complete project documentation | Project documents | Planned | — | Baseline documents created; update with verified results as work proceeds. |
| PM-13 | Organise and publish GitHub repository | Published portfolio repository | Planned | — | Check dataset licence and exclude restricted data before publishing. |
| PM-14 | Review, test, and finalise project | Final quality-checked project | Planned | — | Includes KPI reconciliation and final artifact review. |

Delivery note

Task durations are estimates. If data quality or dashboard work takes longer than planned, prioritise the validated analysis and core dashboard while preserving the 8 days deadline. Record commits as work is completed rather than only at project end.